## Product backlog
UTP CICLO 3 - GRUPO 66
SUBGRUPO 4 AGENDY NAILS
Product Backlog
Sprint 0
Story ID | Story name | Status | Size | Sprint | Priority | Story Type | Comments | Additional Comments
ID01 | Registro Usuarios | Ongoing | 9 | 3 | 3 |  | Se termino de desarrollar el formulario en el sprint 2, se desea que llegue al cliente un correo para que confirme su registro
ID02 | Inicio de sesión de estilistas | Ongoing | 7 | 2 | 2 | Desarrollo | Se termino en el sprit 1 el formulario se esta creando una página donde se le asignen permisos al estilista para que agrege nuevos servicios y mueva su agenda de acuerdo a sus citas disponibles.
ID03 | Inicio de sesión de clientes | Ongoing | 7 | 2 | 2 | Desarrollo | Se termino de desarrollar el formulario en el sprint 2, se esta terminando el carrito de compras en el sprint 3 y se desea trabajar en la pasarela de pago
ID04 | Crear modulo de portafolio de servicios | Done | 6 | 1 | 1 | Desarrollo | Se creo una categorización del portafolio de servicios en el cual se puede ingresar sin estar registrado y se hicieron las conexiones a páginas que amplian la información de cada servicio
ID05 | Clasificar los servicios para categorizarlos (menus) | Ongoing | 5 | 3 | 3 | Desarrollo | Se clasificaron los servicios en galeria de imágenes, portafolio y en la agenda, solo falta terminar la funcionalidad de la agenda.
ID06 | Poder generar una agenda con espacios de turnos | Planned | 9 | 3 | 1 | Desarrollo | Planeado para implementación
ID07 | Modulo de consulta de mis clientes | Ongoing | 6 | 4 | 4 | Desarrollo | Se desea trabajar en una pasarela de pagos donde el cliente pueda cancelar los servicios que desea
ID09 | Definir una sección de noticias | Done | 4 | 1 | 1 | Desarrollo | Ya se definio la sección de noticias
Note on B7: Once a Story ID is given to a story, do not change that number or reuse it even if you delete the story.
Note on D7: Use the following statuses: Planned (or empty) Ongoing Done Removed The sheet uses the above statuses in the formatting and calculation formulas.
Note on E7: Story Points or Ideal Days
Note on F7: Create a release plan by assigning stories to planned sprints. If there are more stories in the backlog than in the plan, leave the remaining stories unassigned to sprints.
Note on G7: You may assign priorities to the stories, but keep in mind that priority does not always equal implementation order.

## Release plan
Increment Plan
Incr. | Start | Days | End | Estimated Size | Real Size | Status | Release Date | Goal | % Esfuerzo vs Estimación
1 | 2021-09-13 | 7 | 2021-09-19 | 10 | 15 | Released | 2021-09-26 | Interfases gráficas de usuario y navegacion entre interfases | 150%
2 | 2021-09-20 | 0 | 2021-09-19 | 14 | 15 | Released | 2021-09-26 | Ir incrementando el bootstrap y los contenedores para diseño responsive | 107.1%
3 | 2021-09-20 | 0 | 2021-09-19 | 0 | 0 | Planned
Sprint Plan
Sprint | Start | Days | End | Estimated Size | Real Size | Status | Release Date | Goal | Increment | % Error estimación
1 | 2021-09-13 | 7 | 2021-09-26 | 10 | 15 | Released | 2021-09-26 | Crear todas las pantallas con HTM y CSS | 1 | 50%
2 | 2021-09-13 | 14 | 2021-09-26 | 14 | 15 | Released | 2021-09-26 | Navegación entre interfases | 1 | 7.143%
3 | 2021-09-20 | 14 | 2021-10-03 | 23 |  | Planned |  |  | 1 | -100%
4 | 2021-09-27 | 14 | 2021-10-10 | 6 |  | Planned |  |  | 2 | -100%
5 | 2021-10-04 | 7 | 2021-10-10 | 0 |  | Planned |  |  | 2 | #DIV/0!
6 | 2021-10-11 | 14 | 2021-10-24 | 0 |  | Planned |  |  | 3
Unplanned
Unplanned
Unplanned
Unplanned
Unplanned
Unplanned
Unplanned
Unplanned
Unplanned
|  |  | Unallocated stories | #VALUE!
|  |  | Total Size | 53 | 30
Formulas:
Start = IF(OR(B16="",[Incr.]=""),"",B16)
Start = IF([Incr.]="","",[Start, row above]+[Days, row above])
End = IF(OR([Start]="",[Days]=""),"",[Start]+[Days]-1)
End = IF(AND([Start]<>"",[Days]<>""),[Start]+[Days]-1,"")